## Gantt Sheet
Hitachi 2 Gantt Chart | [7 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
[5 empty] | Display Week | 1 |  | Week 0 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
[8 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12
 | time axis 2025-02-03 to 2025-05-18
ID | TASK | LEAD | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-02-03 to 2025-05-18
1 | Data Extraction |  |  | - |  |  | -
1.1 | Find Publically Available Lyrics API | Daniel | 2025-02-23 | 2025-02-23 | 1 | 100% | 1
1.2 | Set-up Github Repo and documentation | Jay | 2025-03-10 | 2025-03-11 | 2 | 100%
1.3 | Create Program to Gather Lyric Data | Daniel | 2025-02-25 | 2025-03-01 | 5 | 100% | 4
1.4 | Integrate Spotipy MetaData into Dataset | Daniel | 2025-03-06 | 2025-03-16 | 11 | 100% | 7
1.5 | Rework/Troubleshooting Lyric-Gathering Program | Daniel | 2025-03-17 | 2025-03-18 | 2 | 100% | 2
1.6 | Investigate additional metadata options | Daniel | 2025-04-03 | 2025-04-03 | 1 | 100% | 1
1.7 | Increase Scope of Data | Daniel | 2025-04-03 | 2025-04-06 | 4 | 100% | 2
1.8 | Create Web-Scraper for tsort.info | Daniel | 2025-04-01 | 2025-04-06 | 5 | 100% | 3
1.9 | Fully Automated Program | Daniel | 2025-04-06 | 2025-04-10 | 5 | 100% | 4
2 | Data Cleaning |  |  | - |  |  | -
2.1 | Clean Data in Pentaho | Daniel | 2025-03-06 | 2025-03-17 | 12 | 100% | 1 | bar: 2025-03-06 to 2025-03-17
2.2 | Perform Regular Expressions in Python | Daniel | 2025-04-03 | 2025-04-06 | 4 | 100% | 2 | bar: 2025-04-03 to 2025-04-06
2.3 | Cleaned lyrics for test dataset | Jay | 2025-02-13 | 2025-02-15 | 3 | 100% | 2
2.4 | Defined vector components | Andrew, Kebba | 2025-03-05 | 2025-03-05 |  | 100% | 1
2.5 | Integrated vectors into Pinecone | Andrew , Kebba | 2025-03-13 | 2025-03-13 |  | 100% | 1
2.6 | Completed working vector | Andrew | 2025-03-31 | 2025-03-31 |  | 100% | 1
2.7 | Refine vectors | Andrew | 2025-04-06 | 2025-04-08 |  | 25% | 1
2.8 | Restructure and Reorganize all code and documentation within GitHub to run | Daniel | 2025-04-17 | 2025-04-24 | 7 | 100% | 3
3 | Pinecone Vectorization |  |  | - |  |  | -
3.1 | Index Creation Pipeline in Pentaho | Jay | 2025-03-22 | 2025-03-26 | 5 | 75% | 3
3.2 | Vectorization Pipeline in Pentaho | Jay | 2025-03-28 | 2025-04-02 | 6 | 75% | 4
3.3 | Developed index creation and vectorization workflow using cURL/CMD Prompt | Jay | 2025-03-13 | 2025-03-16 | 4 | 100% | 2
3.4 | Explored test pipeline for Pinecone, from index creation to analysis | Jay | 2025-04-10 | 2025-04-16 | 7 | 100% | 5
3.5 | Developed full end-to-end pipeline for Pinecone | Andrew | 2025-04-01 | 2025-04-24 | 24 | 100% | 18
4 | Visualization/UI |  |  | - |  |  | -
4.1 | Performed exploratory visualizations on test dataset | Jay, Kebba | 2025-02-13 | 2025-02-15 | 3 | 100% | 2
4.2 | Perform analysis/create aggregations | Jay, Kebba | 2025-04-06 | 2025-04-13 | 8 | 0% | 5
4.3 | Create Cluster Visualizations | Daniel | 2025-04-17 | 2025-04-22 | 5 | 100% | 4
4.4 | Create Radial Visualizations | Daniel | 2025-04-22 | 2025-04-22 | 1 | 100%
4.5 | Create Bonus Visualizations | Andrew, Daniel, Jay | 2025-04-22 | 2025-04-23 | 2 | 100%
4.6 | Create working application to test final product with public | Kebba | 2025-04-04 | 2025-04-24 | 21 | 100% | 15
4.7 | Update, Refine, and Upload Documentation | All | 2025-04-20 | 2025-04-24 | 5 | 10000% | 4
4.8 | Practice Presenting and articulating points for clarity | All | 2025-04-25 | 2025-04-30 | 6 | 0% | 4
4.9 |  |  |  | - |  |  | -
Formulas:
Week 0 = [Week 0, row below]
Week 1 = [Week 1, row below]
Week 2 = [Week 2, row below]
Week 3 = [Week 3, row below]
Week 4 = [Week 4, row below]
Week 5 = [Week 5, row below]
Week 6 = [Week 6, row below]
Week 7 = [Week 7, row below]
Week 8 = [Week 8, row below]
Week 9 = [Week 9, row below]
Week 10 = [Week 10, row below]
Week 11 = [Week 11, row below]
Week 12 = [Week 12, row below]
Week 13 = [Week 13, row below]
Week 14 = [Week 14, row below]